## Admin
project
Sarel |  |  | TESTED BY - Urooz Misbah
(updated-Admin Panel) | [11 empty] | 04-04-2024(updated Web-Site)
Bug I.D | POSTED ON | MODULE | SUB MODULE | BUG TYPE | DESCRIPTION | URL | PRIORITY | Screenshort | QA STATUS | DEVELOPER STATUS | DEVELOPER COMMENTS
Bug_001 | 2024-04-04
Bug_002 | 2024-04-04 | Blog Management | List Of Blogs |  | Action>>Edit& Delete Button not present |  |  | https://prnt.sc/DGl9xvSQlA7u | Open
Bug_003 | 2024-04-04 | User Management | List Of All User |  | Profile Picture not updateing |  |  |  | Open
Bug_004 | 2024-05-04 | Blog Management | Publish New Blog |  | Publish Button Not Working | https://prnt.sc/dgC4PZhcRnN5 |  | https://prnt.sc/bgQHHpY0ALFB | Open
Bug_005 | 2024-05-04 | Blog Management | Publish New Blog |  | Tag Button Giving Error After Entering Tag |  |  | https://prnt.sc/dgC4PZhcRnN5 | Open
Bug_006 | 2024-05-04 | Legislation | list of legislations |  | Sr no:-VNU-1710 change Profile button is missing &View Profile Edit & delete option are missing |  |  | https://prnt.sc/DNdCcYXoMEB8 | Open
Bug_007 | 2024-05-04 | Legislation | list of legislations | [5 empty] | Open
Bug_008 | 2024-05-04 | Legislation | Upload New Environmental Court Order |  | Search by topic/sub-topic Details/After Editing The BUtton Edit button Must change To Save |  |  |  | Open
Bug_009 | 2024-05-04 | Court Order Management | Bulk Upload | [5 empty] | Open
Bug_010 | 2024-08-04 | User Management | List Of All Users |  | Timeframe Not Refreshing With Refresh Button |  |  |  | Open
Bug_011 | 2024-08-04 | User Management | List Of All User | Subscribers /View Profiles | Subscribers /View Profiles/When Clicking On View Profile icon Blank page is Comeing |  |  |  | Open
Bug_012 | 2024-08-05 | User Management | List Of All User | [5 empty] | Open
Bug_013 | 2024-08-06 | Dashboard | Dashboard Statistics |  | Apply button & Refresh Button Should Have Some Space Between them |  | https://prnt.sc/WbWFMpF984Oy |  | Open
Bug_014 | 2024-08-07 | Dashboard | Dashboard Statistics |  | Apply button & Refresh Button Not Working |  |  |  | Open
Bug_015 | 2024-08-08 | User Management | List Of All Users/View Profile/user profile |  | Title Of The Name & ISD Code Of Mobile Number Should Be Present |  |  |  | Open
Bug_016 | 2024-08-09 | User Management | List Of All Users/View Profile/user profile |  | Free Trial Period Details Is A heading |  |  |  | Open
Bug_017 | 2024-08-08 | User Management | List Of All Users/View Profile/user profile |  | Billing Address City ,State ,Postal Code,Country,Designation & Organisation Not present |  |  |  | Open
Bug_018 | 2024-08-08 | User Management | List Of All Users/View Profile/user profile |  | Headig My Account Not mentioned |  |  |  | Open
Bug_019 | 2024-08-08 | user management | list of users |  | profile picture not showing after updateing with the website In list |  |  |  | Open
Bug_020 | 2024-08-08 | user management | list of users>>view profile |  | Admin Unable to Address |  |  |  | Open
Bug_021 | 2024-08-09 | Court Order Management |  |  | TopRight Corner Upload new Court Order "Court "Spelling Incorrect |  |  |  | Open
Bug_022 | 2024-08-09 | Court Order Management | List Of Environmental Court Orders |  | view Detail should Be View Profile |  |  |  | Open
Bug_023 | 2024-10-09 | Court Order Management | Upload New Environmental Court Order |  | Upload button not present on Upload Digest Notes &Upload Court Order Pdf |  |  |  | Open
Bug_025 | 2024-10-09 | User Management | List of Users >>Subscribers |  | user unable toView Profile &View Subscription Details
Bug_026 | 2024-10-09 | LEgislation Management | Edit >>Legislation Detail | https://prnt.sc/MGe-TmVnDGpD | When Clicking On Back Buton Empty apge appears
Bug_027 | 2024-10-09
Bug_028 | 2024-10-09
Bug_029 | 2024-10-09

## Website
Bug I.D | POSTED ON | MODULE | SUB MODULE | BUG TYPE | DESCRIPTION | Screenshort | QA STATUS | DEVELOPER STATUS | DEVELOPER COMMENTS
Web-site
BUg_1 | 29-03-2024 | Home |  | UI | Each Word Of Heading Should Be in Capital Letter | https://prnt.sc/xuA71sGzQeLU | Open |  | Done
BUg_2 | 29-03-2024 | Home |  | UI | Extra Feature Legislation is added on home page | https://prnt.sc/FZg-1STFdM4k | Open |  | where is extra feature in figma
BUg_3 | 29-03-2024 | Home |  | UI | Extra Dashboard region is provided on home page | https://prnt.sc/KpQ-Stnc5mdy | Open |  | check new url
BUg_4 | 29-03-2024 | Home |  | UI | The colour Frame Of "Its Our World These Are Our Laws.Join Us Is Not Appropriat" | https://prnt.sc/8Y_etJD_FiMD | Open |  | done
BUg_6 | 29-03-2024 | Home |  | UI | 1 year Plan Is Mention 2 Time and 2 year plan is missing | https://prnt.sc/I8CnLUpHNhwv | Open |  | Done
BUg_7 | 29-03-2024 | Home |  | UI | In 3 year plan (s) is missing | https://prnt.sc/A3bQezOZQ9EP | Open |  | It can be edited by admin
BUg_8 | 29-03-2024 | Home |  | UI | Mobile Icon not Looking Perfect | https://prnt.sc/HhUpXRYMi3WN | Open |  | please provide image
BUg_9 | 29-03-2024 | Sign-up | Register As Free User | UI | First Name Text Columb Not Provided | chat.openai.com/auth/login | Open
BUg_10 | 29-03-2024 | Sign-up | Register As Free User | UI | Last Name Columb not present | chat.openai.com/auth/login | Open
BUg_11 | 29-03-2024 | Sign-up | Register As Free User | UI | Please Enter Mobile Number if you intend to use Sarel Mobile App Check Box Missing | https://prnt.sc/fXiHbGyF3DEG | Open |  | It is there
BUg_12 | 29-03-2024 | Sign-up | Register As Free User | UI | Mobile Number Text Field Is Missing | https://prnt.sc/q3E8foI1iFZb | Open |  | done
BUg_13 | 29-03-2024 | Sign-up | Register As Free User | UI | Country State & City Field Is Missing | https://prnt.sc/kCx4v-NP4Zu2 | Open |  | Done
BUg_15 | 29-03-2024 | Verifyotp | Verify Otp | UI | Start Free Access Button missing | https://prnt.sc/5tRBnCngNC1L | Open |  | done
BUg_16 | 29-03-2024 | Verifyotp | Verify Otp | UI | In Place Of 6 Digit OTP 4 Digit OTP is Comeing | https://prnt.sc/CWBZxKdN7Zyk | Open |  | It will be 4 digits
BUg_18 | 29-03-2024 | Verifyotp | Verify Otp | UI | Resend OTP should Not be In Box | https://prnt.sc/Tj2KXcg0Y-TL | Open
BUg_19 | 29-03-2024 | Verifyotp | Verify Otp | UI | Extra Feature Of Did't recive code is present | https://prnt.sc/c6S5Byt0taNI | Open |  | Done
BUg_20 | 29-03-2024 | Verifyotp | Verify Otp |  | User Is Not able to navigate to Congrtualtions Page |  | Open
BUg_21 | 29-03-2024 | Log In |  | UI | Lost Your Password Can Be "Forgot Your Password" | https://prnt.sc/MzM_AeOhCc2- | Open |  | Done
BUg_22 | 29-03-2024 | Log In |  | UI | Sign In with Facebook & sign In With Google Must Be Two Diffrent Icon | https://prnt.sc/ptch337i9_H3 | Open
BUg_23 | 29-03-2024 | Log In |  | UI | Password View Eye Icon Should be Present | https://prnt.sc/0Hs28Z_GXFJo | Open
(updated Web-Site)
Bug I.D | POSTED ON | MODULE | SUB MODULE | BUG TYPE | DESCRIPTION | Screenshort | QA STATUS | DEVELOPER STATUS | DEVELOPER COMMENTS
BUG_01 | 2024-04-30 | My Account | My Profile |  | Unable To Upload/Change Profile Picture | https://prnt.sc/5yZ2qzHf3oem | Open | Fix
BUG_02 | 2024-05-01 | login your account |  |  | Password Field Sh0uld Contain View Button | https://prnt.sc/za-28eXv2dDu | Open | Done
BUG_03 | 2024-05-02 | Home | sub modules |  | In Sub Modules judgment should be added | https://prnt.sc/jwalD-qR_0bx | Open | New Changes
BUG_04 | 2024-05-03 | Home |  |  | Search Button Not working | https://prnt.sc/dOk95bWd9zwQ | Open | New Changes
BUG_05 | 2024-05-04 | Home | SubHeading("It's our world. These are our laws. This is our work. Join us.") |  | FrameAnd Format Does Not Match The Requirement | https://prnt.sc/FclDHD4CsloS | Open | Open
BUG_06 | 2024-05-04 | Home |  |  | The Plan Name & Number Are Incorrect | https://prnt.sc/Ayagkra7uoKc | Open | Open | Name number added by admin
BUG_07 | 2024-05-04 | Home |  |  | The Space Between Two Blog Sample Should be Less &The Font Should Be Less | https://prnt.sc/six-1oW5_v0D | Open | Open | UI
BUG_08 | 2024-05-04 | Home |  |  | The Extra Feature of Design & pattern Are Mention | https://prnt.sc/O6iCkJ1IcFIE | Open | Open | UI
BUG_09 | 2024-05-04 | Login |  |  | In Place Of Lost Your Password Forget Password Is Mention | https://prnt.sc/O6iCkJ1IcFIE | Open | Fix | Done
[7 empty] | Open | Open
BUG_11 | 2024-05-04 | Verify OTP |  |  | The Otp Need TO be Of 6 Digit | https://prnt.sc/-y6kS-EfAcrp | Open | Open | It is not required,
BUG_12 | 2024-05-04 | Complete Your Profile |  |  | It is Extra Module should come in Register Page | https://prnt.sc/anPoUhdbRRjG | Open | Open
BUG_13 | 2024-05-04 | Complete Your Profile |  |  | mobile Number field Should Also Contain ISD code Field | https://prnt.sc/Rpi2JcG-FQZQ | Open | Open
BUG_14 | 2024-05-04 | Complete Your Profile |  |  | Start Free Access Is Mention As Start Free Trail | https://prnt.sc/S1RpXNWAGqCC | Open | Fix
BUG_15 | 2024-08-04 | Complete Your Profile |  |  | Email -Address &ISD code Missing |  | Open | Open
BUG_16 | 2024-08-04 | Log in To Sarel |  |  | View Eye Icon Should Be Inside the Password Field | https://prnt.sc/fVdfvul-HDj- | Open | Open
BUG_17 | 2024-08-04 | My Account | My Profile |  | Enter Postal Code Unlimited Amount of Digits Are accepted By the Postal Code Field | https://prnt.sc/fbaYMs1XxXUu | Open | Open
BUG_18 | 2024-08-04 | My Account | My Profile |  | user Is Unable to Edit Profile fields | https://prnt.sc/czM4iwuPMd76 | Open | Open
BUG_19 | 2024-08-04 | My Account | My Profile |  | E-mail Id Text Field unable to click |  | Open | Open
BUG_20 | 2024-08-04 | My Account | My Profile |  |  |  | Open | Open
BUG_21 | 2024-12-04 | Register | Complete Your Profile |  | ISD Code Should Be their in mobile text field | https://prnt.sc/AvWst_GK9E6e | Open | Open
BUG_22 | 2024-12-04 | Register | Login |  | View Password icon should be inside the password text box | https://prnt.sc/08V7b_xN1Lcj | Open | Open
BUG_23 | 2024-12-04 | Register | Login |  | User Unable to Loging 1st time after registering |  | Open | Open
BUG_24 | 2024-12-04 | Register |  |  | User Unable to signin usig facebook or google |  | Open | Open
BUG_25 | 2024-12-04 | Log in | OTP |  | resend otp button should be working | https://prnt.sc/u_jgj5bpJ7c0 | Open | Open
BUG_26 | 2024-12-04 | Home |  |  | Blog Aligment is not proper | https://prnt.sc/vPG5rubK_Hhg | Open | Open
BUG_27 | 2024-12-04 | Home |  |  | Subscription added newly are not comeing properly | https://prnt.sc/iqYKEW_C77AC | Open | Open
BUG_28 | 2024-12-04 | Home |  |  |  |  | Open | Open
BUG_29 | 2024-12-04 | Home |  |  | Search Button Not working | https://prnt.sc/DCsQhidHpdoc | Open | Open
BUG_30 | 2024-12-04 | Legislation |  |  | Category Dropdown is not comeing | https://prnt.sc/yiuj5dCq_sCs | Open | Open
BUG_31 | 2024-12-04 | Home
BUG_32
BUG_33
BUG_34
BUG_35
BUG_36
BUG_37

## APP
Sarel Bug Sheet version-1.0
Sareal APP |  |  | TESTED BY - Urooz Misbah
Bug I.D | POSTED ON | MODULE | SUB MODULE | BUG TYPE | DESCRIPTION | PRIORITY | Screenshort | QA STATUS | DEVELOPER STATUS
BUG_001 | 22-0302024 | Register Now | Register | UI | In Place Of Mobile Number E-mail ID Text Field is provided |  | Doc Updated |  | Fix
BUG_002 | 22-03-2024 | Register Now | step2/Enter name and E-mail id | UI | In Place Of E-mail ID ,Mobile Number text field is provided |  | Doc Updated |  | Fix
BUG_003 | 22-03-2024 | Register Now |  | UI | After registering new user congratulations Feature is missing |  | Fix
BUG_004 | 22-03-2024 |  |  | UI | In login Page Below OR Extra codeing is showing in app |  | Open
BUG_005 | 26-02-2024 | Subscription Personal Detail |  | UI | Below Renew Plan Free Trail Is Missing |  | Fix |  | Fix
BUG_006 | 26-02-2024 | Subscription Personal Detail | Subscription payment detail | UI | Subscription Payment Histoy Button Is not available |  | Fix |  | Fix
BUG_007 | [8 empty] | Doc Updated | data coming from backend
BUG_008 | 26-02-2024 | My Plan (Option) | Payment Detail | UI | Continue Button Not clickable |  | Fix |  |  | no UI
BUG_009 | 26-02-2024 | Profile |  | UI | Subscription Spelling Is Wrong |  | Fix |  | Fix
BUG_010 | 26-02-2024 | Profile | My Profile | UI | Designation & Organisation Option Is Missing |  | Doc Updated
BUG_011 | 26-02-2024 | Settings | Change Password | UI | In Current Password PlaceHolder Enter New Password Is Mentioned |  | Fix |  | Doc Updated | not a bug
BUG_012 | 26-02-2024 | Settings | Change Password | UI | User is Unable To Change Password And the Suggestion Notification Is Not Understandable |  | Fix |  | Fix | not a bug
BUG_013 | 26-02-2024 | Settings |  |  |  |  | Fix |  | Fix
BUG_014 | 26-02-2024 | Register Now | 2024-01-03 | UI | Mobile Number Text Field Is Replaced By Email-ID Text Field |  | Fix
BUG_015 | 26-02-2024 | Register Now | 2/3 ENter Name & Email ID | UI | E-Mail Id Text Field Is Replaced By Mobile Number Text Field |  | Fix |  | Fix
BUG_016 | 26-02-2024 | login | Forgot password | UI | Everyplace were the change your pasword need to be their Forgot your passwrd is mentioned |  | Fix |  | Fix | test as per flow
BUG_017 | 26-02-2024 | Forgot Password | Forgot password | UI | Change Password Button Is mention As Forgot Password |  | Open |  | Fix
BUG_018 | 26-02-2024 | Forgot Password | Congratulation | UI | Notification your password has been change properly |  | Open |  | Fix | backend issue
BUG_019 | 26-02-2024 | Register Now |  |  | After Registration For free Trail COgratulations Page Not Displaying |  | Fix |  | Fix | backend issue
BUG_020 | 26-02-2024 | My Plan | My Current Plan |  | Subscription Payment History Button Is Missing& Below Plan Name Free Trail Is In Small Latter |  | Fix |  | Fix | backend issue
BUG_021 | 26-02-2024 | My Plan | Renew /Subscription Plan | buy Subscription/Billing Address/Payment Details | Payment Gateway Page Not Available |  | feature not added |  | Fix
BUG_022 | [6 empty] | Open |  | Fix | as per ui
BUG_023 | [6 empty] | Open |  | Fix
BUG_024
BUG_025 | 28-03-2024 | Forgot Password |  | UI | Forgot Password Button should be change password |  | https://prnt.sc/L24JQrswBjFx | Open | Fix
BUG_026 | 28-03-2024 | Forgot Password | Congratulation | UI | Massage your Password Has been Change Sucessfully Is Incorrect |  | https://prnt.sc/pH3iif_dvuIk | Open |  | as per ui
BUG_027 | 28-03-2024 | Home | Register User | UI | Congratulation pop Up Is Missing |  | https://prnt.sc/HCJTOCq69FFb | Open | Fix
BUG_028 | 28-03-2024 | Home | My Plan |  | App Close By Clicking On My PLan |  | https://prnt.sc/OEbXrPJkNAlg | Fix
BUG_029 | 28-03-2024 | Setting | change password | UI | Space between Confirm Password and change password button is less |  | https://prnt.sc/R9jUsVNJ1u4J | Open | Fix
BUG_030 | 28-03-2024 | Register User | Enter Name And Email ID(2/3) | UI | The title is Incorrect |  | https://prnt.sc/s55TcTpaVYhh | Open
BUG_031 | 28-03-2024 | Register User | Login To Sarel | UI | After the User Is register the login page Contain extra Coding |  | https://prnt.sc/eEmchOpVfw5z | Open |  | that is on time password
BUG_032
BUG_033 | 05--4-2024 | find by court name | year from-year to | Functional | Contail Year Only upto 2000 |  |  | Open | Fix | as per guidelines
BUG_034 | 2024-05-04 | Home | Find ByCourt Name |  | app is closeing when clicking on search button |  |  | Open | Fix
BUG_035 | 2024-05-04 | Search By Legislation | Select Country |  | The Select Category Must Also Have search Option |  |  | Open | Fix
BUG_036 | 2024-04-04 | My Account |  |  | Profile Picture Not Uploading |  |  | Open | Open | bucket account is not provided
BUG_037 | 2024-09-04 | Home | Find By Word Search |  | user is not able to search by country |  |  | Open | Fix | because data is not available
BUG_038 | 2024-09-04 | Home | Find By Word Search |  |  |  |  | Open | Open
BUG_039 | 2024-09-04 | splash Screen | 3rd screen |  | Login Button should not be their |  |  | Fix | Fix
BUG_040 | 2024-09-04 | Home | Search By Word & All The category |  | Category Dropdown Not showing the List added InAdmin Panel |  |  | Open | Fix | backend issue
BUG_041 | 2024-09-04 | Home | Find By law |  | select area radio button not proper |  |  | Open | Fix
BUG_042 | 2024-09-04 | Home | Free Trail Period | congratulations Pop-Up | Free Trail Period "Date is static" |  |  | Open | Fix
BUG_043 | 2024-09-04 | Home | Find By Law |  | Year from Year to should enable add text |  |  | Open | Fix
BUG_044 | 2024-09-04 | Home | Find By Law |  | Year Dropdown Should Be More |  |  | Open | Fix
BUg_47 | 2024-09-05 | Home | My Profile |  | Billing Address & Edit Button Overlapping |  |  | Open | Fix
BUg_48 | 2024-09-05 | Home/Profile | Subscription |  | Heading All The Words Should Be Capital |  |  | Open | Fix
[8 empty] | Open | Fix
BUg_50 | 2024-09-05 | Profile | Subscription |  | select last plan >>Payment Detail>>select Payment options>>select terms &conditons>>when Clicking On Continue button its not working |  |  | Open | Fix
BUg_51 | 2024-10-05 | home | Subscription |  | when adding new subscription plan its not reflecting in app |  |  | Open | Open | flow change
BUg_52 | 2024-10-05 | home | Find By citation |  | on Selecting Journal Law app is closeing |  |  | Open | Fix
BUg_53 | 2024-10-05 | home | Search Legislations |  | Back Arrow Button overlapping With Heading |  |  | Open | Fix | attach screenshot
BUg_54 | 2024-10-05 | home | blog |  | when uploading blog one time from admin 4-5 time is showing in phone |  |  | Open | Fix | not a bug
BUg_56 | 2024-10-05 | home
BUg_57 | 2024-10-05 | home
BUg_58 | 2024-10-05 | home
BUg_59 | 2024-10-05 | home
BUg_60 | 2024-10-05 | home
BUg_61 | 2024-10-05 | home
BUg_62
BUg_63
BUg_64
BUg_65
BUg_66
BUg_67
BUg_68
BUg_69